## Sheet1
| Sat - 31 | Sun - 1 | Mon - 2 | Tue - 3 | Wed - 4 | Thu - 5 | Fri - 6 | Sat -7 | Sun - 8 | Mon - 9 | Tue - 10 | Wed - 11 | Thu - 12
Task | [13 empty] | K - Kelvin
Complete proposal | Sat - 31: Done | T- Thao
Schedule and Tasks deligation | [13 empty] | M -May | bar: Sat - 31
Create Master and Branches | [13 empty] | Y - Yijing | bar: Sat - 31
Data Extraction (csv, api) | [13 empty] | A - All | bar: Sat - 31
Crude export data from US - CSV | Sat - 31: Done
Crude export data from CA - CSV | Sat - 31: Done
USD/CAD exchange rate - API | Sat - 31: Done
GDP from oil export from US | bar: Sat - 31
GDP from oil export from CA | bar: Sat - 31
Renewable energy production from US | bar: Sat - 31
Renewable energy production from CA | bar: Sat - 31
Data Transform | bar: Sun - 1 to Thu - 5
Data Analysis and Plotting | bar: Fri - 6 to Mon - 9
PPT slides | bar: Tue - 10
Practice presentation | bar: Wed - 11
Class/ Merge time | bar: Sat - 31; Tue - 3; Thu - 5; Sat -7; Tue - 10
Deadline | bar: Thu - 12